## Project Planner
Sprint 3 - Agility
Select a period to highlight at right. A legend describing the charting follows. | [5 empty] | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | STAFF MEMBER(S) | PLAN START (Hours) | PLAN DURATION (Hours) | ACTUAL START (Hours) | ACTUAL DURATION (Hours) | PERCENT COMPLETE | PERIODS
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Develop a plan (Gantt chart) | All team members | 1 | 2 | 1 | 2 | 0%
Build requirements table | Chris | 3 | 2 | 3 | 1 | 0%
Create requirements signoff table | Chris | 3 | 1 | 3 | 1 | 0%
Write the algorithm | Gianna | 4 | 2 | 4 | 1 | 0%
Create the staffing plan | Chris | 4 | 1 | 4 | 1 | 0%
Create the block code | Gianna | 6 | 4 | 5 | 2 | 0%
Create the flowchart | Gianna | 10 | 2 | 7 | 2 | 0%
Get the sensor data diagram | Gianna | 12 | 2 | 9 | 2 | 0%
Create the test table | Chris | 12 | 2 | 11 | 1 | 0%
Write the System Design Document | All team members | 14 | 3 | 11 | 3 | 0%
Take a video of the robot | Gianna | 17 | 1 | 14 | 1 | 0%
Upload items to the Github repository | All team members | 18 | 1 | 15 | 1 | 0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%